## Work Items
ID | Title | Type | Priority | Start Date | End Date | Status | YYYY-Week | YYYY-MM | YYYY | Cycle Time (days) | Current Age (days) | URL | Done ≤ 1 day | Done ≤ 7 days | Done ≤ 14 days | Done ≤ 21 days | Done ≤ 28 days
DONE-96 | Fix performance regression in the data processing pipeline | Bug | Highest | 2025-10-14 | 2025-10-25 | Done | 2025-W43 | 2025-10 | 2025 | 12 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-26 | Resolve memory leak in the background job processing worker | Bug | High | 2025-10-22 | 2025-11-02 | Done | 2025-W44 | 2025-11 | 2025 | 12 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-13 | Redesign the reporting dashboard with filterable date ranges | Bug | Medium | 2025-10-26 | 2025-11-13 | Done | 2025-W46 | 2025-11 | 2025 | 19 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-128 | Fix intermittent timeout errors in the third-party API client | Bug | Low | 2025-10-28 | 2025-11-02 | Done | 2025-W44 | 2025-11 | 2025 | 6 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | TRUE | TRUE | TRUE | TRUE
DONE-126 | Add audit logging for all user actions in the admin interface | Bug | High | 2025-11-06 | 2025-11-16 | Done | 2025-W46 | 2025-11 | 2025 | 11 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-1 | Add internationalization support for the customer-facing UI | Bug | Low | 2025-11-11 | 2025-11-13 | Done | 2025-W46 | 2025-11 | 2025 | 3 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | TRUE | TRUE | TRUE | TRUE
DONE-56 | Add GraphQL API endpoint for the mobile application team | Bug | High | 2025-11-16 | 2025-11-29 | Done | 2025-W48 | 2025-11 | 2025 | 14 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-28 | Add support for custom fields in the customer profile section | Bug | High | 2025-11-19 | 2025-11-22 | Done | 2025-W47 | 2025-11 | 2025 | 4 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | TRUE | TRUE | TRUE | TRUE
DONE-77 | Add automated regression tests for the payment processing flow | Bug | Medium | 2025-11-22 | 2025-11-30 | Done | 2025-W48 | 2025-11 | 2025 | 9 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-75 | Add dark mode support to the main application interface | Bug | Medium | 2025-11-24 | 2025-11-26 | Done | 2025-W48 | 2025-11 | 2025 | 3 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | TRUE | TRUE | TRUE | TRUE
DONE-146 | Add support for multiple currency display in the pricing tables | Bug | Medium | 2025-12-02 | 2025-12-19 | Done | 2025-W51 | 2025-12 | 2025 | 18 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-7 | Add comprehensive API documentation using OpenAPI specification | Bug | Low | 2025-12-05 | 2025-12-09 | Done | 2025-W50 | 2025-12 | 2025 | 5 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | TRUE | TRUE | TRUE | TRUE
DONE-50 | Implement soft-delete functionality across all resource endpoints | Bug | High | 2025-12-06 | 2025-12-26 | Done | 2025-W52 | 2025-12 | 2025 | 21 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-98 | Add comprehensive end-to-end tests for the checkout flow | Bug | Medium | 2025-12-08 | 2025-12-23 | Done | 2025-W52 | 2025-12 | 2025 | 16 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-2 | Improve search indexing performance for large datasets | Bug | Low | 2025-12-14 | 2025-12-24 | Done | 2025-W52 | 2025-12 | 2025 | 11 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-117 | Implement automated data export with configurable scheduling | Bug | Medium | 2025-12-16 | 2026-01-03 | Done | 2026-W01 | 2026-01 | 2026 | 19 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-48 | Create data migration scripts for the legacy customer records | Bug | Medium | 2025-12-18 | 2026-01-02 | Done | 2026-W01 | 2026-01 | 2026 | 16 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-57 | Improve error handling and retry logic in the email delivery service | Bug | Medium | 2025-12-20 | 2025-12-21 | Done | 2025-W51 | 2025-12 | 2025 | 2 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | TRUE | TRUE | TRUE | TRUE
DONE-30 | Implement two-factor authentication for privileged user accounts | Bug | Medium | 2025-12-24 | 2026-01-07 | Done | 2026-W02 | 2026-01 | 2026 | 15 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-60 | Implement webhook delivery with exponential backoff retry | Bug | Medium | 2026-01-01 | 2026-01-16 | Done | 2026-W03 | 2026-01 | 2026 | 16 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-65 | Implement smart caching strategy for frequently accessed resources | Bug | Medium | 2026-01-03 | 2026-01-23 | Done | 2026-W04 | 2026-01 | 2026 | 21 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-31 | Implement configurable rate limiting for the public REST API | Bug | Low | 2026-01-07 | 2026-01-20 | Done | 2026-W04 | 2026-01 | 2026 | 14 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-137 | Implement GDPR-compliant data deletion workflow for user accounts | Bug | Low | 2026-01-13 | 2026-01-28 | Done | 2026-W05 | 2026-01 | 2026 | 16 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-135 | Refactor the notification service to use an event-driven pattern | Bug | Highest | 2026-01-17 | 2026-01-26 | Done | 2026-W05 | 2026-01 | 2026 | 10 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-88 | Resolve slow startup time caused by heavy dependency loading | Bug | High | 2026-01-22 | 2026-02-06 | Done | 2026-W06 | 2026-02 | 2026 | 16 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-91 | Fix performance regression in the data processing pipeline | Bug | Low | 2026-01-28 | 2026-02-11 | Done | 2026-W07 | 2026-02 | 2026 | 15 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-118 | Resolve memory leak in the background job processing worker | Bug | Medium | 2026-01-31 | 2026-02-11 | Done | 2026-W07 | 2026-02 | 2026 | 12 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-116 | Redesign the reporting dashboard with filterable date ranges | Bug | Medium | 2026-02-06 | 2026-02-18 | Done | 2026-W08 | 2026-02 | 2026 | 13 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-69 | Fix intermittent timeout errors in the third-party API client | Bug | Low | 2026-02-10 | 2026-03-01 | Done | 2026-W09 | 2026-03 | 2026 | 20 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-21 | Add audit logging for all user actions in the admin interface | Bug | Lowest | 2026-02-14 | 2026-02-15 | Done | 2026-W07 | 2026-02 | 2026 | 2 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | TRUE | TRUE | TRUE | TRUE
DONE-100 | Add internationalization support for the customer-facing UI | Bug | Medium | 2026-02-18 | 2026-03-08 | Done | 2026-W10 | 2026-03 | 2026 | 19 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-102 | Add GraphQL API endpoint for the mobile application team | Bug | Medium | 2026-02-21 | 2026-03-02 | Done | 2026-W10 | 2026-03 | 2026 | 10 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | TRUE | TRUE | TRUE
DONE-41 | Add support for custom fields in the customer profile section | Bug | Medium | 2026-02-25 | 2026-03-14 | Done | 2026-W11 | 2026-03 | 2026 | 18 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-32 | Add automated regression tests for the payment processing flow | Bug | High | 2026-02-26 | 2026-03-16 | Done | 2026-W12 | 2026-03 | 2026 | 19 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
WIP-15 | Implement streaming data pipeline for real-time analytics processing | Bug | High | 2026-02-27 |  | In Progress |  |  |  |  | 79 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-48 | Migrate all frontend components from JavaScript to TypeScript | Bug | High | 2026-02-27 |  | In Progress |  |  |  |  | 79 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
DONE-10 | Implement GDPR-compliant data deletion workflow for user accounts | Bug | High | 2026-03-01 | 2026-03-21 | Done | 2026-W12 | 2026-03 | 2026 | 21 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | FALSE | FALSE | TRUE | TRUE
DONE-83 | Implement automated database backup and point-in-time recovery | Bug | High | 2026-03-02 | 2026-03-07 | Done | 2026-W10 | 2026-03 | 2026 | 6 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | TRUE | TRUE | TRUE | TRUE
DONE-55 | Add comprehensive API documentation using OpenAPI specification | Bug | High | 2026-03-04 | 2026-03-08 | Done | 2026-W10 | 2026-03 | 2026 | 5 |  | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv | FALSE | TRUE | TRUE | TRUE | TRUE
WIP-41 | Build the self-service onboarding wizard for new enterprise customers | Bug | Medium | 2026-03-07 |  | In Progress |  |  |  |  | 71 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-39 | Add support for pluggable storage backends in the file service | Bug | Low | 2026-03-10 |  | In Progress |  |  |  |  | 68 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-12 | Migrate the test suite from RSpec 2 to RSpec 3 and fix all failures | Bug | High | 2026-03-13 |  | In Progress |  |  |  |  | 65 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-50 | Implement service mesh with mutual TLS for inter-service communication | Bug | Medium | 2026-03-16 |  | In Progress |  |  |  |  | 62 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-14 | Build automated load testing harness for the API performance suite | Bug | Medium | 2026-03-18 |  | In Progress |  |  |  |  | 60 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-9 | Build the self-healing infrastructure automation for cloud resources | Bug | Medium | 2026-03-20 |  | In Progress |  |  |  |  | 58 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-32 | Build the partner API portal with usage analytics and rate limiting | Bug | Low | 2026-03-23 |  | In Progress |  |  |  |  | 55 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-29 | Implement serverless functions for the image transformation pipeline | Bug | Low | 2026-03-26 |  | In Progress |  |  |  |  | 52 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-43 | Refactor the notification dispatcher to support pluggable channels | Bug | Medium | 2026-04-02 |  | In Progress |  |  |  |  | 45 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-8 | Build the new incident management dashboard with on-call scheduling | Bug | Low | 2026-04-06 |  | In Progress |  |  |  |  | 41 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv
WIP-1 | Build the customer health score algorithm for the success team | Bug | High | 2026-04-11 |  | In Progress |  |  |  |  | 36 | file:///home/cbroult/work/ruby/predictability-engine/data/samples/sample_data_large.csv